## Slide 1: Work Breakdown Structure

## Slide 2
SW
Project
SCOPE
Planning
Requirements
Design
Development
Testing
Built
Release
Deployment
UAT
Operation
Maintenance

## Slide 3: Project Management
Planning
Estimating
Scheduling
Define activities & deliverables
Time, Cost in terms of resource usage
Define sequence of tasks occurrence

## Slide 4: Why is it needed?
Create WBS
Estimation techniques
Identify dependencies
For task identification
Using graph/network diagram
Create Tasks Schedule
Gantt. Chart
W.r.t size & efforts (i.e. Software productivity)
Reduced chances of project failure
Fails because of incomplete tasks’ quotation

## Slide 5: What is WBS?
a work breakdown structure is:
  “A hierarchical decomposition
  of the total scope of work
  to be carried out by the project team
  to accomplish the project objectives
  and create the required deliverables.”

## Slide 6: WBS
Dividing complex projects to simpler and manageable tasks.
Stops till the tasks no longer remains decomposable.
Work packages are the smallest unit of work that a project can be broken down into when creating your Work Breakdown Structure (WBS).
A WBS element may be a product, data, a service, or any combination.
6

## Slide 7: WBS
The WBS is a deliverable-oriented hierarchy / activity-oriented hierachy of decomposed project components.
Articulates the detailed project scope statement that specifies the work to be accomplished by the project.
WBS

## Slide 8: When should we develop WBS?
Once the project Scope is decided then its needed to plan various components (activities/deliverables) of software development project.

## Slide 9: How to create WBS?
Done by project mangers mostly
Determine and describe the project statement
Highlight all necessary phases in the project
  Sometimes the scope is divided to different phases depending upon project
  Lowest level not too detailed, not too large
Create deliverables
Check for completeness - is all the effort included?
Assign deliverables to each team
9

## Slide 10: WBS

## Slide 11: WBS
WBS

## Slide 12: Reasons to use WBS
It helps with the correct project organization.
It depicts whole project work needed for org.
It assists in describing the project scope to stakeholders.
It helps to distribute responsibilities.
Visualize each member’s activity & role in project.
It shows the project milestones and all the points to control.
Helpful in cost estimation, resource allocation, and time management improvements.
Minimize unnecessary work which leads to missed deadlines & scope creep issues

## Slide 13: Steps to build a WBS
Begin with the Charter, focusing on Objectives and Deliverables
Break the main product(s) down into sub-products
Set the structure to match how you’ll manage the project
Lowest level not too detailed, not too large
Identify support activities
Check for completeness - is all the effort included?
Assign work package to managers
13

## Slide 14: Levels in WBS
Starts with level 0 i.e. project title
Then make level 1, highest level breakdown of about 4-7 nodes depending on your project. Termed as control accounts
Then make level 2 are work packages.
Level 3 are the tasks/activities to be performed
Follow the standard numbering scheme
14

## Slide 15: WBS levels
Library management Systems
Database
Front end application
Servers configuration
data structures used
Database creation
UI design
……
ER diagram

## Slide 16: WBS Formats
2 Formats
Outline (Indented Format)
Graphical Tree (Organizational Chart)

## Slide 17: Displaying the WBS Example of outlined WBS.
17

## Slide 18: Displaying the WBS Example of Graphical Tree WBS
18

## Slide 19
https://online.visual-paradigm.com/diagrams/features/work-breakdown-structure-software/

## Slide 20: Challaenges
Must have concrete knowledge of project
All tasks/ deliverables properly identified and quoted
Each task should be broken down into legit activities
20

## Slide 21: The Dictionary of the WBS
WBS
A WBS dictionary is a companion document to the WBS that describes each WBS element. For each WBS element, the WBS dictionary includes a statement of work, a list of associated activities, and a list of milestones.
Other information can include the responsible organisation, start and end dates, resources required.

## Slide 22: WBS Guidelines
22
Must be easy to understand
Ensure each element corresponds to a deliverable
Breakdown until you get accurate time and cost estimates
Covers all objectives

## Slide 23: WBS Guidelines
23
Should not be much detailed as project plan
May use a template if you have
Can evolve over time
Can be drawn using Gantt Pro, Word, Excel, MS Project, Visio etc.
Each level have no more than 7 items

## Slide 24: WBS Template
Component groups with a ‘+’ in front of them are ‘rolled up’ – subcomponents are hiden to reduce clutter
24

## Slide 25: WBS Check List
Does it define 100% of the work that will be produced by the project?
Does it use a coding structure so that each element has a unique ID that shows its place in the hierarchy e.g. 1.1, 1.2, 1.1.1, 1.1.2?
Will project stakeholders be able to understand the project scope from the WBS?
Does each level represent 100% of the work required to deliver the parent level?
Is the decomposition sufficient that the tasks required to deliver each work package can easily be identified?
Is it in the format that gives a clear graphical, textual or tabular breakdown of the project scope?
25

## Slide 26: WBS Check List
Does it have a least two levels with at least one level of decomposition?
Was it created by those who will be performing the work?
Is it being regularly updated as project changes are approved?
Can you identify one person who is accountable for each work package?
Can you clearly define the acceptance criteria for each work package?
Does it allow you to estimate costs accurately?
Does the WBS have logical summary elements that can be used in tracking progress and performance?
26

## Slide 27: Example WBS
Redecorate Room
  Prepare materials
    Buy paint
    Buy a ladder
    Buy brushes/rollers
    Buy wallpaper remover
  Prepare room
    Remove old wallpaper
    Remove detachable decorations
    Cover floor with old newspapers
    Cover electrical outlets/switches with tape
    Cover furniture with sheets
  Paint the room
  Clean up the room
    Dispose or store left over paint
    Clean brushes/rollers
    Dispose of old newspapers
    Remove covers
WBS

## Slide 28: Professional Tools used
https://www.projectmanager.com/
https://www.atlassian.com/software/jira
https://ganttpro.com/